## README
Last Update | 2018-10-03
Author | Logan Crocker
Email | lcroc001@ucr.edu
Description | This is the SCRUM document for our team "Give Me Five". All of our sprint progress will be updated here.
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means by "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Minimize task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
1 | Registration | As an unregistered customer who is insterested in the app, I want to register an account so that I can login the app | 3 | 1 | done
2 | Login/Logout | As a registered user, I want to login my account with user name and password, and logout my account to end the session | 1 | 2 | login done
3 | Share | As a user, I can share my photos by making a post. I can add tags and a description to my posts | 2 | 3 | done
4 | Profile | As a user, I want to edit my profile so that my followers can view my information | 4 | 4 | done
5 | Follow | As a user, I can follow other users and view their posts in my feed | 2 | 5 | done
6 | Like | As a user, I can like other peoples' posts | 1 | 6
7 | Comment | As a user, I can leave comments on other posts or reply to existing comments. | 2 | 7
8 | Favorite | As a user, I can favorite posts and view them in my favorites gallery | 3 | 8
9 | Followers | As a user, other users can follow me and I can view who follows me | 2 | 9 | still need to view followers
10 | Password update | As a user, I can change my password if I want to | 4 | 10 | in progress
11 | Delete account | As a registered user, I can delete my account if I no longer wish to use the app. | 8 | 11 | probably needs to be split
12 | Notifications | As a registered user, I can receive notifications from my posts, such as likes or comments | 5 | 12 | might not do this now
13 | Photo processing | As a registered user, I can process a photo before posting it, such as adding filters or text. | 5 | 13
14 | Recommendation | As a user, I can view a feed of posts that only have a certain tag | 8 | 14 | Due to firebase limitations, changing it to a system where we can "discover" posts based on filtering by a tag
| Total |  | 50
Note on C2: Acceptance Criteria: 1. I can select the register button 2. I can create a profile with a username and password
Note on C3: Acceptance criteria: 1. I can use my username and password to log into the app
Note on C4: Acceptance criteria: 1. I can upload an image from my phone gallery 2. I can add a description to my posts 3. I can view my posts on my profile
Note on C5: Acceptance criteria: 1. I can modify all of my profile info such as name, location, etc.
Note on C6: Acceptance criteria: 1. I can select the follow button on someone's account 2. I can view their posts in my feed
Note on C7: Acceptance criteria: 1. I can select the like button on someone's post
Note on C8: Acceptance criteria: 1. I can comment on a post 2. I can reply to comments
Note on C9: Acceptance criteria: 1. I can favorite a post 2. I can view my favorites on my profile
Note on C10: Acceptance criteria: 1. I can view who follows me
Note on C11: Acceptance criteria: 1. I can change my password
Note on C12: Acceptance criteria: 1. I can delete my account
Note on C13: Acceptance criteria: 1. When someone performs an action with my posts, I get a notification 2. I can turn off notifications
Note on C14: Acceptance criteria: 1. I can add filters to my posts 2. I can add text to my posts
Note on C15: Acceptance criteria: 1. I can view recommended posts based on my most frequent tags 2. The recommendation page is separate from my profile page

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
Task 1: Login page design
Task 2: Registration functionality
Task 3: Login functionality
Task 4: Profile page design
Task 5: Posting functionality
Task 6: Can edit contents of profile
Task 7: Can follow other users
Task 8: Design layout of feed
Task 9: Liking posts
Task 10: Commenting on posts
Task 11: Favoriting posts
Task 12: Add favorites gallery to profile page
Task 13: View who follows me
Task 14: Change password
Task 15: Delete account
Task 16: Send notifications
Task 19: Feed based on a selected tag
Task 20: Log out functionality
Note on C2: Design the login page, including the registration link Acceptance Criteria: 1. XXX 2. XXX
Note on B3: Design a table for storing user accounts Acceptance Criteria: 1. xxx 2. xxx 3. xxx

## Archives
Sprint ID | Scrum Master | Tasks Completed
.. | .. | ..
Note on C2: Design the login page, including the registration link

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
1 | 50 | 0 | 0 | 50 | 26