## README
Last Update | 2018-11-28
Author | Logan Crocker
Email | lcroc001@ucr.edu
Description | This is the SCRUM document for our team "Give Me Five". All of our sprint progress will be updated here.
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means by "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Minimize task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
1 | User Account | As an unregistered customer who is insterested in the app, I want to register an account so that I can login the app, I want to login my account with user name and password, and logout my account to end the session | 7 | 1 | done
2 | Profile | As a user, I want to edit my profile so that my followers can view my information | 7 | 2 | done
3 | Share | As a user, I can share my photos by making a post. I can add tags and a description to my posts | 7 | 3 | done
4 | Folowing | As a user, other users can follow me and I can view who follows me | 3 | 4 | done
5 | Follow | As a user, I can follow other users and view their posts in my feed. | 3 | 5 | done
6 | Like | As a user, I can like other peoples' posts | 4 | 6 | done
7 | Comment | As a user, I can leave comments on other posts or reply to existing comments. | 4 | 7 | done
8 | Search | As a user, I can search people whose name I know | 4 | 8 | done
9 | Photo processing | As a registered user, I can process a photo before posting it, such as cut it. | 4 | 9 | done
10 | Recommendation | As a user, I can view a feed of posts that only have a certain tag | 7 | 10 | Due to firebase limitations, changing it to a system where we can "discover" posts based on filtering by a tag
| Total |  | 50
Note on C2: Acceptance Criteria: 1. I can select the register button 2. I can create a profile with a username and password
Note on C3: Acceptance criteria: 1. I can modify all of my profile info such as name, location, etc.
Note on C4: Acceptance criteria: 1. I can upload an image from my phone gallery 2. I can add a description to my posts 3. I can view my posts on my profile
Note on C5: Acceptance criteria: 1. people follow me can see my feed
Note on C6: Acceptance criteria: 1. I can select the follow button on someone's account 2. I can view their posts in my feed
Note on C7: Acceptance criteria: 1. I can select the like button on someone's post
Note on C8: Acceptance criteria: 1. I can comment on a post 2. I can reply to comments
Note on C9: Acceptance criteria: 1. I can search user's name to visit their profole 2.I can follow them after searching
Note on C10: Acceptance criteria: 1. I can add filters to my posts 2. I can cut posts
Note on C11: Acceptance criteria: 1. I can view recommended posts based on my most frequent tags 2. The recommendation page is separate from my profile page

## Task Board
To Do (Sprint Backlog) |  | In Progress | Testing | Done
Sprint1:different pages design | Login page design |  |  | Task 1: Login page design
| profile page design |  |  | Task 2: profile page design
camera page design
| database design |  | learn firework
Sprint2:different pages functions | Register |  |  | Task 3: register
| Log in/Log out |  |  | Task 4: Log in/Log out
| edit profile |  | scale posts after click on it | Task 5: Can edit contents of profile
| post processing |  |  | Task 6: crop posts and add filters in posts
edit database
Sprint3: Posting | Crop a rectangle from image
| search page design |  |  | Task 7: search page design
| post page design |  |  | Task 8: post page design
| new feed page design |  |  | Task 9: new feed page design
Sprint4:link database | store posts to database |  |  | Task 10: store posts to database
| edit profile in database |  |  | Task 11: edit profile
| follow other users,other users follow me |  |  | Task 12: follower &following
| search posts and users in database |  |  | Task 13: search posts and users in database
| add tags |  |  | Task 14: Add tag
| show posts from database in profile |  |  | Task 15: show my posts
Sprint5:new feed & Debug | view followers' posts in new feed page |  |  | Task 16: view new feeds
| save comments to database and shows on UI | Change the number of comments after posted |  | Task 17: comments on posts
| like posts |  |  | Task 18: like posts
| debug codes and fix |  |  | Task 19: debug
| UI design |  | change button image after clicking
Note on B2: design a login page Acceptance Criteria: 1. page looks suitable logan
Note on D2: Design the login page, including the registration link Acceptance Criteria: 1. XXX 2. XXX
Note on E2: logan
Note on B3: design a profile page Acceptance Criteria: 1. page looks suitable linyun zhang
Note on E3: linyun zhang
Note on B4: try to use camera or gallery yun li yifan zhao
Note on B5: learn how to use database xinyue zhao
Note on B6: new user can register after click on the rigister button logan
Note on E6: logan
Note on B7: user can log in with email and password, they can also log out logan
Note on E7: Logan Crocker
Note on B8: user can change their name, profile,description,email linyun zhang
Note on E8: linyun zhang
Note on B9: edit picture from camera or from gallery yun li yifan zhao
Note on E9: yun li yifan zhao
Note on B10: start to create a database and link it to activity xinyue zhao
Note on B11: Microsoft Office User: Yun Li
Note on B12: creat a suitable search page yun li yifan zhao
Note on E12: yun li yifan zhao
Note on B13: create a post page with post picture, descroption, tags xinyue zhao
Note on E13: xinyue zhao
Note on B14: create a new feed page with a profile, username,post picture,like and comment button linyun zhang
Note on E14: linyun zhang
Note on B15: xinyue zhao
Note on E15: xinyue zhao
Note on B16: change profile,name,description. logan
Note on E16: Logan linyunzhang
Note on B17: follow others
Note on E17: logan
Note on B18: discover 1.search people with name 2.search post with tag logan
Note on E18: logan xinyue zhao
Note on B19: xinyue zhao
Note on E19: xinyue zhao
Note on B20: read all of user's posts and show them in the profile
Note on E20: Logan linyun zhang
Note on B21: after follow others, can see their feed in the new feed page. xinyue zhao
Note on E21: xinyue zhao logan
Note on B22: yun li
Note on C22: Microsoft Office User: Yun Li
Note on E22: yun li yifan zhao
Note on B23: linyun zhang logan
Note on E23: logan
Note on E24: Yun Li Yifan Zhao
Note on B25: improve design 1.scale picture size 2.change button image linyun zhang

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | Logan Crocker | Task 1,2
2 | Linyun Zhang | Task 3,4,5,6
3 | Yun Li | Task 7,8,9
4 | Xinyue Zhao | Task 10,11,12,13,14,15
5 | Yifan Zhao | Task 17,18,19
Note on C2: different pages design,including log in, profile, camera
Note on C3: different pages functions,including log in,log out,register, post processing
Note on C4: some tasks about posting, including new post page, new feed page,search post page
Note on C5: things about database, store things in database and read things in database
Note on C6: edit new feed,including like and comment. Fix some bugs improve the app UI

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
1 | 50 | 6 | 6 | 44 | 40
2 | 50 | 12 | 18 | 32 | 30
3 | 50 | 7 | 25 | 25 | 20
4 | 50 | 17 | 42 | 8 | 10
5 | 50 | 8 | 50 | 0 | 0